LONE ROCK POINT

AI Builder Day

What it is and how to run one

A reusable playbook for organizing an internal, hands-on AI build day.

# What an AI Builder Day is

An AI Builder Day is a focused, internal “hackathon” — one day set aside for the whole team to stop, experiment, and build something real with AI. It is not a training course, a webinar, or a day of reading and tutorials. The entire premise is to learn by building.

People spend most of the day heads-down on a project of their own choosing, supported by a shared chat channel and a couple of group touchpoints. The day ends with everyone demoing what they made. Polish is explicitly not the point — momentum, confidence, and shared discovery are.

The one rule that matters: Don’t spend the day learning about AI. Spend it building with AI. The goal is to come away having made something, however rough.

## Why we do it

A Builder Day moves the team along the AI adoption curve through hands-on experience rather than mandate. Four strategic goals drive it:

- Boost confidence with AI — increase the team’s comfort with AI tooling and methods across every discipline.

- Spark adoption — encourage everyday use of new AI tools across all processes and roles.

- Accelerate workflows — push prototyping and experimentation earlier in the product life cycle.

- Build culture — start evolving toward an AI-native culture through shared, hands-on experimentation.

It works because it pairs a light top-down nudge (everyone participates and demos) with a bottom-up culture of exploration (you pick what to build). Over time these events help a team move from a few early adopters to an early majority, and they surface new, concrete possibilities for the business.

## Who it’s for

Everyone — product, design, engineering, data, marketing, operations, leadership. Cross-functional participation is a feature, not a complication: the most interesting demos often come from non-engineers automating their own day-to-day work.

## What “good” looks like

- Every participant shows up with at least a rough idea and leaves having built something they can demo.

- Demos show real things working “in action,” not slides about ideas.

- The team leaves with a shared inventory of where AI is already used and where the highest-value gaps are.

- People feel more confident reaching for AI tools the following Monday.

# The day, hour by hour

Below is the standard Builder Day shape — roughly a six-hour day with two heads-down build blocks bracketing a group exercise, then demos. Adjust the clock to your timezone and team; keep the structure.

| Time | Block | What happens |
| --- | --- | --- |
| 10:30–11:00 | Opening Ceremonies | Brief intro from the host. Round robin: each participant quickly states what they’re going to try to build. |
| 11:00–1:00 | Build Time | Heads-down work on your plan. Stay connected in the shared channel for questions and help. |
| 1:00–1:45 | AI Inventory Exercise (Optional) | Group exercise: catalogue where AI is already used across the company, discuss gaps, and identify high-value opportunities. |
| 2:00–3:30 | Build Time | More heads-down work. Wrap up enough to have something you can show during demos. |
| 3:30–4:30 | Demos & Wrap-up | Everyone shares what they built (screen-share, show-and-tell). Final discussion and takeaways. |

Tip: run all coordination through a single dedicated channel (e.g. #builderday) and drop the video-call link there for the group blocks.

## The two group blocks, explained

### Opening Ceremonies

Keep it short — 30 minutes. The host frames the why and the ground rules, then a fast round robin where each person says, in a sentence or two, what they intend to build. Saying it out loud creates accountability and sparks ideas in others.

### AI Inventory Exercise (Optional)

A 45-minute group discussion mid-day. Together, list everywhere AI is currently being used across the company, name the gaps, and flag the highest-value opportunities where AI could make a real impact. This produces a lasting artifact and often reshapes what people build in the afternoon.

### Demos & Wrap-up

The payoff. Everyone screen-shares and shows what they built. Close with a group discussion of takeaways: what surprised people, what they’d build next, what the team should adopt.

# What to build

The guidelines are deliberately loose, but there are guidelines. The aim is to go beyond chatting with an AI like a glorified search box, and instead build something with a bit of structure and reuse to it.

- Go beyond a single prompt. Don’t stop at one-off questions — build something repeatable.

- Automate a burden. Think about the tedious, recurring things in your day-to-day work. What could you build that eases that burden?

- Enhance something you already do. Take an existing task and make it faster, better, or higher-quality with AI.

- Build a skill or a chain of skills that executes a process in a repeatable way.

Idea starters: a reusable “skill” that drafts a recurring report; an automation for a copy/paste-heavy task; a tool that summarizes meetings into action items; an assistant that triages incoming requests; a prototype that explores a product idea you’ve never had time to test.

# How to get ready

A good Builder Day starts before the day. The single biggest predictor of a productive day is that people arrive knowing roughly what they want to build — not wondering how to spend the time.

## For participants

- Think in advance about what you want to build. Don’t plan to spend the day reading or doing tutorials — plan to build.

- Pick something real — a burden to automate or a task to enhance (see “What to build”).

- Share a short briefing ahead of time. By close of business a couple of days before, reply to the kickoff thread with an idea or two. This is mostly about accountability and arriving ready to go.

- Set up your tools — make sure you have access to whatever AI tools, accounts, and environments you’ll need so you’re not blocked on day one.

## For the organizer

- Pick a date and block the full day on everyone’s calendar. Protect it from meetings.

- Send a kickoff message a week or so out: the why, the agenda, the “what to build” guidance, and a request for everyone to reply with an idea by a set deadline.

- Create the shared channel (e.g. #builderday) for coordination, help, and the video-call link.

- Prepare the opening framing — the strategic goals and ground rules — and a simple round-robin order.

- Line up tool access and a support path so people who get stuck can get unblocked quickly.

- Plan the demo flow — order, timing, and who facilitates the closing discussion.

- Capture the AI inventory during the group exercise and save it somewhere durable for follow-up.

# Demo guidelines

Demos are the heart of the day. Set the tone so people share freely and without anxiety.

- Do share your screen. Show the thing itself.

- It doesn’t need to be polished. This isn’t a client demo — you’re among friends.

- Show it “in action,” not as slides. No screengrabs or decks; demo what you actually built.

- Don’t fear the “demo fail.” It happens to everyone. It won’t be the first time and it won’t be the last.

- Keep it to ~10 minutes max, including Q&A and discussion.

# Facilitation tips & AI techniques

## Running the day well

- Protect the heads-down blocks. Resist the urge to fill them with check-ins; the shared channel is enough.

- Keep the group blocks tight. Start and end on time so build momentum isn’t lost.

- Normalize asking for help in the channel — pairing and quick assists make the day better for everyone.

- Recognize effort. Some teams add light prizes or shout-outs to celebrate what people made.

## Effective AI interaction techniques to share

A couple of practical techniques worth passing along to participants who hit walls:

- Be specific and quantitative. When a model isn’t giving you what you want, use precise modifiers to help it calibrate — e.g. “be 100x more harsh” or “be 20% nicer.”

- Start fresh when stuck. If a prompt keeps failing, clearing the agent’s context and starting over is often more efficient than trying to repair the existing path.

## Adoption beyond a single day

Builder Days are most powerful as a recurring ritual rather than a one-off. Successful AI adoption blends a top-down mandate (everyone participates and demos) with a bottom-up culture of exploration (you choose what to build). Run them on a cadence, keep the AI inventory alive between sessions, and use each demo day to decide what the team should adopt for real.

# Appendix: Quick-start checklist

## 1–2 weeks before

- Set the date; block the full day on calendars.

- Send the kickoff message (why, agenda, what-to-build guidance, idea deadline).

- Create the shared #builderday channel.

## A few days before

- Participants reply to the thread with an idea or two.

- Confirm tool/account access for everyone.

- Prepare opening framing and round-robin order.

## Day of

- Opening ceremonies + round robin.

- Build block 1.

- AI inventory group exercise (capture the list).

- Build block 2.

- Demos + wrap-up discussion and takeaways.

## After

- Save the AI inventory and demo takeaways somewhere durable.

- Decide what to adopt for real; schedule the next Builder Day.